## Sheet1
Time Estimate for Project Name
SL No | Project | Phase | Project Module | Project Sub Module | Progress | Hours Total 50 | Start Date | End Date | Proposed End Date | Status
1 | Pet Care System | Design Phase | User | Login | Login Page contains username and password with a login button that helps to log into the application on the user side | 2 | 2022-07-25 | 2022-07-25 |  | Completed
2 | Pet Care System | Design Phase | User | Registration | Registration page contains all the details of user which mainly contains user name, password, which helps at the time of login | 3 | 2022-07-26 | 2022-07-26 |  | Completed
3 | Pet Care System | Design Phase | Admin | Admin home page | Admin page contains view users, add details of puppy clinic, add veterinery doctor,vaccination details, view feedback | 1 | 2022-07-27 | 2022-07-27 |  | Completed
4 | Pet Care System | Design Phase | User | User home page | User page contains my profile, add dogs, details of vaccination, buy puppies, sell puppies, feedback, find breeding partner, veterinery doctor, details of pet clinic | 1 | 2022-07-27 | 2022-07-27 |  | Completed
5 | Pet Care System | Design Phase | User | Profile page | Profile page contains name, age, address, email, phone number | 2 | 2022-07-28 | 2022-07-28 |  | Completed
6 | Pet Care System | Design Phase | User | About/ Contact us | Added details of contact and about details of the system | 2.5 | 2022-07-30 | 2022-07-30 |  | Completed
7 | Pet Care System | Design Phase | Admin | Login for admin | Using servlet admin can enter the home page using admin user name and password and corrected some errors inside the module. | 2.5 | 2022-08-02 | 2022-08-02 |  | Completed
8 | Pet Care System | Design Phase | User | My Profile | Clearing errors(issue on adding profile picture) | 1.5 | 2022-08-03 | 2022-08-03 |  | Completed
9 | Pet Care System | Development Phase | User | User registration | Adding the data to the database | 2 | 2022-08-05 | 2022-08-05 |  | Completed
10 | Pet Care System | Design Phase | Admin | Add veterinery doctor | Add veterinery doctor page contains name, address, phone number, email, location, experiene | 2 | 2022-08-05 | 2022-08-05 |  | Completed
11 | Pet Care System | Development Phase | Admin | Add veterinery doctor | Adding the data to the database | 2 | 2022-08-05 | 2022-08-05 |  | Completed
12 | Pet Care System | Design Phase | Admin | Add vaccination | Add vaccination contain days form birth, vaccination name, breed, description | 2 | 2022-08-06 | 2022-08-06 |  | Completed
13 | Pet Care System | Development Phase | Admin | Add vaccination | Adding the data to the database | 2 | 2022-08-06 | 2022-08-06 |  | Completed
14 | Pet Care System | Design Phase | User | Add feedback | Add feedback contains name, feedback | 2 | 2022-08-07 | 2022-08-07 |  | Completed
15 | Pet Care System | Development Phase | User | Add feedback | Adding the data to the database | 2 | 2022-08-07 | 2022-08-07 |  | Completed
16 | Pet Care System | Development Phase | Admin | View user | Adding the data to the database | 2 | 2022-08-07 | 2022-08-07 |  | Completed
17 | Pet Care System | Design Phase | Admin | View feedback | Designing view feedback page | 1 | 2022-08-11 | 2022-08-11 |  | Completed
18 | Pet Care System | Development Phase | Admin | View feedback | Viewing feedback table content | 1 | 2022-08-11 | 2022-08-11 |  | Completed
19 | Pet Care System | Design Phase | User | Sell puppies | Adding details of puppy selling details | 1 | 2022-08-14 | 2022-08-14 |  | Completed
20 | Pet Care System | Development Phase | User | Sell puppies | Adding data to database | 1 | 2022-08-14 | 2022-08-14 |  | Completed
21 | Pet Care System | Design Phase | Admin | Selling request | Viewing details of selling request | 2 | 2022-08-15 | 2022-08-15 |  | Completed
22 | Pet Care System | Development Phase | Admin | Selling request | Taking data from database | 1 | 2022-08-16 | 2022-08-16 |  | Completed
23 | Pet Care System | Development Phase | User | Register | Validation using jsp | 2 | 2022-08-17 | 2022-08-17 |  | Completed
24 | Pet Care System | Development Phase | User | Login | Validation using jsp | 2 | 2022-08-17 | 2022-08-17 |  | Completed
25 | Pet Care System | Development Phase | User | User home page | Session management | 2 | 2022-08-18 | 2022-08-18 |  | Completed
26 | Pet Care System | Development Phase | Admin | Admin home page | Session management | 1 | 2022-08-18 | 2022-08-18 |  | Completed
27 | Pet Care System | Development Phase | User | Registration | Form validation | 2 | 2022-08-19 | 2022-08-19 |  | Completed
28 | Pet Care System | Development Phase | User | Registration | Email validation and adding captcha | 2 | 2022-08-19 | 2022-08-19 |  | Pending
29 | Pet Care System | Development Phase | User | All modules | Adding html page with title having app logo | 1 | 2022-08-19 | 2022-08-19 |  | Completed
30 | Pet Care System | Development Phase | User | All modules | Alert messages | 1 | 2022-08-20 | 2022-08-20 |  | Completed
31 | Pet Care System | Development Phase | User | All modules | Clearing errors | 4 | 2022-08-20 | 2022-08-20 |  | Completed
32 | Pet Care System | Development Phase | User | Registration | Adding Email validation | 3 | 2022-08-21 | 2022-08-21 |  | Completed
33 | Pet Care System | Development Phase | Admin | User list | Adding bootstrap table | 1 | 2022-08-21 | 2022-08-21 |  | Completed
34 | Pet Care System | Development Phase | Admin | View feedback | Adding bootstrap table | 1 | 2022-08-21 | 2022-08-21 |  | Completed
35 | Pet Care System | Development Phase | Admin | View selling request | Adding bootstrap table | 1 | 2022-08-21 | 2022-08-21 |  | Completed
36 | Pet Care System | Development Phase | Admin | Registration | Google integration | 1 | 2022-08-22 | 2022-08-22 |  | Pending
37 | Pet Care System | Development Phase | Admin | Registration | Email validation | 1 | 2022-08-22 | 2022-08-22 |  | Completed
38 | Pet Care System | Development Phase | Admin | Registration | Registration | 1 | 2022-08-22 | 2022-08-22 |  | Completed
39 | Pet Care System | Development Phase | User | Selling puppies | Clearing errors | 1 | 2022-08-22 | 2022-08-22 |  | Completed
40 | Pet Care System | Development Phase | Admin | Registration | Google integration | 1 | 2022-08-23 | 2022-08-23 |  | Pending
41 | Pet Care System | Development Phase | User | My Profile | Fetching values | 2 | 2022-08-23 | 2022-08-23 |  | Completed
42 | Pet Care System | Development Phase | User | All modules | Clearing errors | 2 | 2022-08-23 | 2022-08-23 |  | Completed
42 | Pet Care System | Development Phase | User | Sell puppies | Uploading data to database | 2 | 2022-08-24 | 2022-08-24 |  | Completed
42 | Pet Care System | Development Phase | User | My Profile | View and edit user information | 1 | 2022-08-24 | 2022-08-24 |  | Completed
43 | Pet Care System | Development Phase | Admin | View selling request | Adding request status | 2 | 2022-08-25 | 2022-08-25 |  | Completed
44 | Pet Care System | Development Phase | User | View selling status | Viewing request status | 1 | 2022-08-25 | 2022-08-25 |  | Completed
44 | Pet Care System | Development Phase | User | My Profile | Uploading profile photo | 3 | 2022-08-26 | 2022-08-26 |  | Completed
45 | Pet Care System | Design Phase | User | Sell puppies | Photo uploading | 2 | 2022-08-27 | 2022-08-27 |  | Completed
46 | Pet Care System | Development Phase | User | Sell puppies | Photo uploading | 2.5 | 2022-08-27 | 2022-08-27 |  | Completed
47 | Pet Care System | Design Phase | User | My Profile | Photo uploading | 1 | 2022-08-28 | 2022-08-28 |  | Completed
48 | Pet Care System | Development Phase | User | My Profile | Photo uploading | 2 | 2022-08-28 | 2022-08-28 |  | Completed
49 | Pet Care System | Development Phase | User | Show puppies | Photo uploading | 1 | 2022-08-29 | 2022-08-29 |  | Completed
50 | Pet Care System | Development Phase | User | Selling status | Photo uploading | 1 | 2022-08-29 | 2022-08-29 |  | Completed
51 | Pet Care System | Development Phase | Admin | User details | Photo uploading | 1 | 2022-08-29 | 2022-08-29 |  | Completed
52 | Pet Care System | Development Phase | Admin | Selling request | Photo uploading | 1 | 2022-08-29 | 2022-08-29 |  | Completed
53 | Pet Care System | Design Phase | User | Buy puppy | Adding fields to display data | 1 | 2022-08-30 | 2022-08-30 |  | Completed
54 | Pet Care System | Development Phase | User | Buy puppy | Getting data from database | 1 | 2022-08-30 | 2022-08-30 |  | Completed
55 | Pet Care System | Design Phase | User | Payment | Adding fields to display data | 1 | 2022-08-30 | 2022-08-30 |  | Completed
56 | Pet Care System | Development Phase | User | Payment | Payment processing | 1 | 2022-08-30 | 2022-08-30 |  | Completed
57 | Pet Care System | Testing Phase | User | All modules | Registration, login, my profile, sell puppy, buy puppy, selling status | 3 | 2022-09-01 | 2022-09-01 |  | Completed